XingKey Tarot v1.1 → v2.0 Optimization Roadmap

Core Design Principles

Based on the current project status and review feedback, the entire plan revolves around three priorities:

Pass review first — resolve the content richness issue to meet app store requirements

Improve retention second — build user stickiness through daily usage and history features

Commercialize last — only explore monetization after reaching specific user thresholds

Each phase has clear acceptance criteria and risk mitigation strategies. No pre-research is conducted without defined trigger conditions.

Phase 0: v1.1 Approval Version (P0 Priority)

Timeline: 10 days including 3 days of buffer

Sole objective: Pass app store review and go live

Feature Expansion Strategy

All three new features reuse the existing card-drawing logic, keeping development effort to a minimum.

Single Card Quick Reading

One-card quick Q&A format, supporting custom questions or direct draws without a question

Displays card image, upright/reversed position, and interpretation

Includes a "View Full Card Meaning" link at the bottom that navigates to the tarot library (the library will be implemented in v1.3; the link serves as a placeholder for now)

Relationship Exploration Spread

Three cards corresponding to: my state, the other person's state, and relationship direction

Completely reuses the Three-card Spread drawing logic, only changing position names and interpretation focus

Development effort is roughly equivalent to modifying a configuration file

Daily Fortune Enhancement

The functionality remains unchanged, but it is given a larger, independent card entry on the home page

Directly displays today's card name and keywords, strengthening the visual perception that this is a standalone feature

Home Page Layout

A three-layer structure ensures that feature richness is immediately visible upon opening the app.

Top section: Daily Fortune large card displaying today's card thumbnail and keyword preview

Middle section (2×2 grid): Single Card Quick Reading, Three-card Spread, Relationship Exploration, and Decision Spread (coming soon placeholder)

Bottom section (tool entries): Tarot Library (placeholder) and History Records (placeholder)

The Decision Spread and Tarot Library use "Coming Soon" placeholders to visually fill the grid without penalizing the review. All feature entries use an "icon + text" card format so reviewers do not perceive them as simple reskins.

Technical Debt Cleanup

Completed concurrently without separate scheduling:

Migrate ImagePacker.packing() to packToData()

Comprehensively clean up deprecated @ohos.* imports and global getContext() calls

Add signing configuration to ensure normal release builds

Compliance Improvements

Unify disclaimer font size, position, and color across all result pages

Dynamically request WRITE_IMAGEVIDEO permission when saving images, with friendly prompts for permission denial

Add version numbers to privacy policy and user agreement documents

App Store Submission Bonus Points

Store screenshots cover four pages: Daily Fortune, Single Card Quick Reading, Three-card Spread, and Relationship Exploration

App description emphasizes self-awareness, tarot beginner learning, and psychological companionship, downplaying the divination attribute

Screenshots themselves serve as proof of content richness

Acceptance Criteria

Home page displays at least 4 independent feature entries

Zero build errors in release mode

Core flows pass on HarmonyOS 6.0 and 6.1 physical devices

All compliance points are covered without omissions

Phase 1: v1.2 History Records + Share Image Integration (P1 Priority)

Timeline: 3 weeks including 3 days of buffer

The two features are released together because the history records experience feels incomplete without share image generation. Combined release creates a complete closed-loop experience in one go.

History Records

Stored in Preferences with key prefix "history_fortune_", capped at 100 entries; oldest records are automatically cleared when exceeded

Covers all divination types: Daily Fortune, Single Card, Three-card Spread, and Relationship Exploration

Supports chronological browsing (newest first), single entry deletion, and one-click clear with secondary confirmation

Each record stores: divination type, timestamp, drawn cards (including upright/reversed status), and interpretation text summary, allowing the history detail page to directly reconstruct results

Share Image Enhancement

Redesigned in black-gold star-moon style, with 2× scale screenshots for improved clarity

Adds a preview popup before saving, supporting both "Save to Album" and "Direct Share" operations

Failure scenarios show Toast prompts with clipboard text fallback, eliminating silent failures

Bidirectional Integration

Divination result pages can directly generate share images

History record detail pages can directly generate share images for the corresponding result

This bidirectional integration is the core value of releasing both features together.

Acceptance Criteria

History records read and write normally, no duplicates or data loss, automatic cleanup works when limit is exceeded

Share image clarity meets standards, visual style is unified

History records to share image flow is closed-loop, no navigation exceptions

Phase 2: v1.3 Tarot Library Learning Module (P1 Priority)

Timeline: 2.5 weeks including 3 days of buffer

This is the key step in product positioning upgrade — from "divination tool" to "tarot beginner learning tool", which benefits both user retention and app store description. All 78 card data already exists; the work is primarily UI and content organization.

Feature Design

Complete 78-card tarot library with categorized browsing: 22 Major Arcana + 4 suits of Minor Arcana (Wands, Cups, Swords, Pentacles), 14 cards each

Single card details display card image, upright/reversed interpretations, and core keywords, with data sourced directly from the existing InterpretationData.ets file

Supports fuzzy search by card name or keywords

Supports favoriting frequently used cards, with state persisted locally

All card names on divination result pages are clickable, navigating directly to the corresponding tarot library detail page, creating a natural "divination → learning" flow

Content Tiering Strategy

Major Arcana (22 cards): Detailed interpretations including card imagery stories, comprehensive upright/reversed explanations, and applicable scenarios

Minor Arcana (56 cards): Start with keywords + simplified interpretations, to be expanded in future versions

Important: Do not let content filling delay the release schedule. A simplified launch is better than chasing perfection.

Acceptance Criteria

All 78 cards are fully displayed, category and search functions work correctly

Divination result → tarot library detail navigation flow is smooth

Favorite states persist after app restart

Phase 3: v1.4 Art Upgrade + Experience Refinement (P2 Priority)

Timeline: 2 weeks including 3 days of buffer

Prerequisite: Development only starts after 22 Major Arcana design drafts are delivered and accepted.

Parallel Art Strategy

Design work proceeds concurrently from Phase 0. First produce one sample draft to confirm the "black-gold star-moon + exquisite fantasy character" style, then batch produce the rest. This does not consume development time. No text is embedded in images; card names and numbers are uniformly overlaid by the app.

Development Content

Replace 22 Major Arcana card images, adapted for multiple resolutions, with smooth loading

Unify card name/number overlay style (position, font, color) across all scenarios: divination, share images, and tarot library

Card flip animations and page transitions, kept restrained to maintain performance on low-end devices

Onboarding guide optimization, with settings page support for re-viewing the guide

Complete loading states, empty states, and error prompts, eliminating all silent failure scenarios

Acceptance Criteria

22 Major Arcana display correctly across all scenarios, no distortion or misalignment

Animations are smooth and lag-free, consistent with the starry aesthetic

No blank pages or unresponsive scenarios throughout the entire flow

Phase 4: v2.0 Pre-research & Launch (P3 Priority)

Hard trigger conditions — both must be met simultaneously. No resources are invested until thresholds are reached:

30 consecutive days of DAU ≥ 500 with 7-day retention ≥ 20%

"AI deep interpretation" requests account for ≥ 30% of user feedback

Upon meeting the conditions, a 2-week pre-research phase begins:

HarmonyOS account service / cloud Preferences synchronization solutions

On-device AI interface compliance assessment

User research on light commercialization paths (theme skins, premium interpretation packs)

Produce technical pre-research documents and compliance reports before deciding whether to proceed

Testing Strategy

For independent developers with limited resources, adopt a "primary coverage + cloud testing supplement" approach:

HarmonyOS 6.0/6.1: Full core feature testing on owned physical devices

HarmonyOS 5.0: Sample verification via Huawei Cloud Test Platform remote devices, covering installation, startup, and core divination flow

Four core test cases must pass before each release:

Complete divination flow

Share image saving to album

Home screen widget refresh

Local storage read/write operations

Risk Mitigation

Art Delivery Delays

Mitigation: Start design work in parallel. Produce one sample draft first to confirm style. Fallback plan: release features first and replace card images later.

Multi-version Compatibility

Mitigation: Prioritize HarmonyOS 6.0/6.1 as primary versions. Use cloud testing sampling for 5.0. Do not pursue perfect adaptation across all versions.

Review Rejection

Mitigation: All new features pass compliance self-check before release. Verify item by item against the submission checklist.

Tarot Library Content Copyright

Mitigation: All interpretation text is originally written or AI-generated with manual proofreading. Marked as "original compilation".

Home Screen Widget Blank Screen

Mitigation: Cache write timing — synchronously write to cache after the first daily fortune generation. Expiration strategy — 24-hour validity period, display placeholder text when expired.

Overall Timeline Summary

The following presents the complete version roadmap. Art design work proceeds in parallel starting now and does not consume any development time.

v1.1 — Core objective: Pass review and go live with 4+ feature entries. Timeline: 10 days. Priority: P0.

v1.2 — Core objective: History records + share image integration. Timeline: 3 weeks. Priority: P1.

v1.3 — Core objective: Tarot library learning module. Timeline: 2.5 weeks. Priority: P1.

v1.4 — Core objective: Art upgrade + experience refinement. Timeline: 2 weeks. Priority: P2.

v2.0 — Core objective: Pre-research after DAU thresholds are met. Timeline: 2-week pre-research after trigger. Priority: P3.